## Slide 1
Coffee County
Capital Improvement Plan
2017 - 2037

## Slide 2
Coffee County
Capital Improvement Plan
2017 - 2037

## Slide 3
(5 Questions, “Yes” or “No” Answers)
Do you know exactly how many buildings that you, as a Commissioner, are responsible for?
Do you know exactly how many HVAC units you have that are running on R22 refrigerant?
Do you know how old the roof on your Courthouse is?
Do you know how many voting houses you have; if the roof is leaking on any of them; how they are heated and cooled; and if the toilets will flush?
Do you know if there is anywhere you can go, or anyone in your County to ask, that can provide you will all the above information?
(NEITHER DID WE)

## Slide 4
Inventory of Buildings
Needs Assessment
Twenty-year Capital Plan
Funding Plan
Charge

## Slide 5
Assigned Asset Numbers
Collected data in 14 major components of each building.
INVENTORY OF BUILDINGS

## Slide 6: NEEDS ASSESSMENT
Current Condition of each component
What needed to be done.
a) When
b) Cost

## Slide 7: TWENTY-YEAR PLAN
Immediate Needs
Anticipated Future Needs

## Slide 8: FUNDING PLAN
Current Financial Condition
a) Debts
b) Debt Service
c) Available Revenue
2. Shuffle Projects to Match Available Funding

## Slide 9: Coffee County Capital Improvement Plan Years 2017 - 2037
Prepared by:
Coffee County Commission
Dean Smith, District 1 and Chairman
Kim Ellis, District 2
Josh Carnley, District 3
Al Britt, District 4
Jimmy Jones, District 5
Jim Thompson, District 6
Tom Grimsley, District 7
Date: October 2016

## Slide 10: THE PLAN
Consideration of Options
a) 18 months
b) 9 Options
Division of Work
a) Energy Savings Projects
b) Capital Improvement Loan Projects
c) Jail and Sheriff Expansion Projects
d) Anticipated Future Projects
Financing
a) General Fund
i) Energy Project
ii) Capital Improvement Loan Projects
iii) Annual Capital Improvement Projects
b) Sheriff and Jail Fund
c) Highway and Engineering Fund
d) Environmental Services Fund
Cash Flow

## Slide 11: LIVING PLAN
Twenty-Year Plan
Accomplishments of Previous Year
Budget for Current Year
Adjustments of plan

## Slide 12
Energy Savings Project
  Completed May 2017
  Cost $3,197,793
  Resealed 10 buildings
  Replaced 2,288 light fixtures
  Replaced 20 HVAC systems
  Installed 126 water saving devices
  Converted phone system from Analog to Digital
Capital Improvement Loan Projects
  Approximately 75% complete
  Spent $619,396 so far
  Estimated completion date December 2017
  Estimated total cost of projects $1,486,100
  Actual Projects
Jail and Sheriff Expansion Projects
  Jail began August 2016
  75% Complete
  Estimated completion of Jail – October 2017
  Cost of Jail expansion is $1,362,070
  Administration Building scheduled to begin – November 2017
  Administration Building estimated completion – March 2018
  Administration Building estimated cost - $400,000
Anticipated Future Projects
2017

## Slide 13
2018

## Slide 14: Projects to Date
Resealed buildings - 10
LED light fixtures - 2,450
HVAC units - 60
Water devices - 147
Phones - 185
Roof projects - 18
Carpet projects - 6
Paint projects - 20
Window projects - 1-49 pieces
Building and renovations - 39,187 sq. ft.

## Slide 15
Questions?

## Slide 17: FY 2017 Annual Projects
Mt. Pleasant: paint/carpet
New Hope: paint
IT: Fujitsu Mini-split
Farm Center Voting Room: Mini-split
Deputy Hut: decks
Mapping & Appraisal: upgrade restroom
Eight polling locations: new a/c’s
Engineer’s Office: paint