## Sheet1
FY 2020 County Transportation Plan
Autauga County
Date Approved by the Autauga County Commission: August 15, 2019
Date Amended by the Autauga County Commission: (If Applicable)
Map Index | Project No. | Road Name/Number | Begin |  | End |  | Project Details |  |  |  | Total Project Estimated Cost | Estimated Amount Planned To Be Utilized Under Competitive Bid | Estimated Amount Planned To Be Utilized Under Public Works | Amount Expended exempt from Competitive and/ or Public Works Contracts | County Rebuild Alabama Funds or Federal Aid Exchange Funds (List fund type separately for projects involving both CRAFs and FAEFs) | CRAF Amount | FAEF Amount
|  |  | Lat. | Long. | Lat. | Long. | Road Improvement Project | Bridge Improvement Project | Project Length (miles) | Description of Work | [7 empty] | Project Length (miles) (This column is used for calculations only and should not be included in the printed document)
[10 empty] | Estimated Beginning Balance | [5 empty] | 0 | 0
[10 empty] | Estimated Annual Revenue | [5 empty] | 800000 | 400000
[10 empty] | Rebuild Funds Received from Municipalities through MOUs | [5 empty] | 0 | 0
1 | RA-ACP 01-01-2020 | Brown St | 32.57 | 86.4 | 33.4 | 86.6 | X |  | 3.1 | Resurfacing and Traffic Striping/Marking from Sunset Dr to SR-14 | 250000 |  | 250000 |  | CRAF | 250000 |  | 3.1
2 | RA-ACP 01-02-2020 | Brasfield Blvd | 33.5645 | 86.6544 | 33.5645 | 86.6544 |  | X | 0.1 | Replacement of Bridge, BIN 010583 at Swift Creek | 200000 |  | 200000 |  | FAEF |  | 200000 | 0
3 | RA-ACP 01-03-2020 | Sunny Ln | 32.49 | 86.355 | 33.5 | 86.435 | X |  | 1 | Leveling and Base Failure Repair From CR-82 to CR-59 | 65000 | 65000 |  |  | CRAF | 65000 |  | 1
3 | RA-ACP 01-04-2020 | Sunny Ln | 32.49 | 86.355 | 33.5 | 86.435 | X |  | N/A | Resurfacing and Traffic Striping/Marking from CR-82 to CR-59 | 125000 |  | 125000 |  | CRAF | 125000 |  | N/A
4 | RA-ACP-01-05-2020 | Progress Way | 33.478 | 86.2525 | 33.495 | 86.253 | X |  | 3 | Resurfacing and Traffic Striping from Sunny Ln to Brown St | 200000 |  | 200000 |  | FAEF |  | 200000 | 3
4 | RA-ACP-01-05-2020 | Progress Way | 33.478 | 86.2525 | 33.495 | 86.253 | X |  | N/A | Strip Patching and Base Work from Sunny Ln to Brown St | 50000 | 50000 |  |  | CRAF | 50000 |  | N/A
4 | RA-ACP-01-05-2020 | Progress Way | 33.478 | 86.2525 | 33.495 | 86.253 | X |  | N/A | Resurfacing and Traffic Striping from Sunny Ln to Brown St | 200000 |  | 200000 |  | CRAF | 200000 |  | N/A
0
0
0
0
Totals/Page Totals |  |  | Total Miles Addressed by CTP (Total Mileage Does Not Include Bridge Projects) | [5 empty] | 7.1 | Total CTP Estimated Costs | 1090000 | 115000 | 975000 | 0 | Total CRAF/FAEF Remaining Estimated | 110000 | 0 | 7.1
Note: Any amendments to the CTP shall follow the same guidelines and procedures as the original approval process.
Remarks |  | Map 2, RA-ACP 01-02-2020 is a Federal Aid Project that will Utilize $800,000 of Federal Aid Funds and $200,000 FAEF
The remaining estimated balance of CRAF will be carried over for projects in next fiscal year's CTP.
CTP Plan 6/06/2019